REDACTED SAMPLE — EXCERPT 3 of 4 — Implementation Roadmap  |  Client-identifying details removed. Analysis and reasoning are unchanged from the delivered engagement. Published with client permission.

FROM A FOUNDATION STRATEGIC PLAN

# 30 / 60 / 90 Day Action Plan

Days 1–30: Foundation & Validation

Finalize written pricing/rate card across all three product tiers

Set up basic business infrastructure (LLC/tax ID if not done, business bank account, simple invoicing)

Create a Google Business Profile and one social channel; upload existing job photos

Formalize the referral agreement with the local referral partner

Reach out to repeat customers for testimonials and referrals

Assess delivery options (truck purchase/rental/trailer) against the starting budget

Days 31–60: Traction & Refinement

Launch active in-season booking against a weekly jobs-in-pipeline target

Begin systematic photo/video documentation of every job for portfolio and social content

Track actual material costs and job time per unit to validate the cost ratio and refine pricing if needed

Request reviews from every completed job

Test one off-season/indoor product concept with a small prototype

Monitor cash flow against the operating reserve target weekly

Days 61–90: Scale Preparation

Evaluate whether current weekly capacity is sufficient for demand; identify if part-time help is needed

Finalize a delivery/logistics solution if not already resolved

Build a simple pre-booking/deposit system for next season’s early slots

Analyze actuals against the financial model; adjust Year 1 forecast assumptions if volume is over or under plan

Decide go/no-go on a winter product line based on the Days 31–60 test results

Set explicit milestone criteria for revisiting the day-job decision